## Main
Today |  |  | 48 |  | 48 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-11-13 |  |  | Hours | Hours | Hours |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
Rank | Task | Assn | Est. | Worked | Rem. |  |  | 13/11 | 14/11 | 15/11 | 16/11 | 17/11 | 18/11 | 19/11 | 20/11 | 21/11 | 22/11 | 23/11 | 24/11 | 25/11 | 26/11 | 27/11 | 28/11 | 29/11 |  | Detailed Information | #
Task Assignments
| Animation | [25 empty] | 5
4 | Red Demon Movements and Animations | K | 2 | 3 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 6
1 | Red Demon's Abilities and Methods of attack | K | 3 | 2 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
3 | Creating the basic appearance and motion of the Red Demon | K | 4 | 3 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2 | Implementation of basic items and traps for fleeing humans to use | K | 3 | 2 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
3 | Programming the player character's movements and basic operations (moving, running, crouching, etc.) in the game | K | 3 | 2 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
4 | 3D modeling of the Red Devil character model and creation of animations for specific actions and movements | K | 4 | 2 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
7
| Design | [25 empty] | 5
4 | AI and Movement design of fleeing humans | T | 3 | 2 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 9
3 | Design of Maps and Environments | T | 4 | 3 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 10
5 | Red Demon Appearance and Design | T | 3 | 1 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 11
2 | Detailed design of AI and movements of fleeing humans | T | 3 | 1 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
4 | Enhanced tracker mode behaviour adapted to the map and environment | T | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
3 | Environmental design of specific locations in the game and programming of the player's movement in those environments | T | 3 | 2 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
17
| Sound | [25 empty] | 5
3 | Creating sound effects and background music | K | 3 | 2 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 19
4 | Additional sound effects | K | 2 | 1 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 20
21
| Mechanic | [25 empty] | 5
1 | Game mechanics and story progression for the player to become the perpetrator | T | 2 | 3 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 23
2 | Implementation of additional game mechanics for the player to be the perpetrator | T | 1 | 1 | 1 |  | 1 | [17 empty] | 1 | bar: Mon to Wed
2 | Programming new game mechanics for the player to be the perpetrator | T | 3 | 2 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
24
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Sprint Settings – Only change cells with dark gray borders | [7 empty] | Mon: Workdays |  |  | 101
| Kazuya | K |  | Start Date | 2023-11-06 |  |  | Mon: Sun; Tue: 0; Wed: 0 |  |  | 102
| Taiyo | T |  | End Date | 2023-11-17 |  |  | Mon: Mon; Tue: 1; Wed: 1 |  |  | 103
| Name3 | 3 | [5 empty] | Mon: Tue; Tue: 1; Wed: 1 |  |  | 104
| Name4 | 4 |  | Total Days | 11 |  |  | Mon: Wed; Tue: 1; Wed: 1 |  |  | 105
| Name5 | 5 |  | Work Days | 0 |  |  | Mon: Thu; Tue: 1; Wed: 1 |  |  | 106
| Name6 | 6 | [5 empty] | Mon: Fri; Tue: 1; Wed: 3 |  |  | 107
| Name7 | 7 | [5 empty] | Mon: Sat; Tue: 0; Wed: 0 |  |  | 108
| Name8 | 8 | [24 empty] | 109
| Name9 | 9
| Name10 | 10
|  |  |  | Lookback | 4 | [21 empty] | 110
Interpreted Data – DO NOT CHANGE ANYTHING HERE | [26 empty] | 111
| Current Hours Remaining |  |  |  |  | Days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 112
[6 empty] | On-Track Line | 48 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | 113
114
[6 empty] | Sum | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 |  | 115
| Rank (and not reduced to 0 after today) | [25 empty] | 116
| Rank 1 - The MOST important | 1 |  |  |  | Rank 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 117
|  | 2 |  |  |  | Rank 2 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 118
|  | 3 |  |  |  | Rank 3 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 |  | 119
|  | 4 |  |  |  | Rank 4 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 |  | 120
| Rank 5 - The LEAST important | 5 |  |  |  | Rank 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 121
[6 empty] | Sum | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 |  | 122
123
[6 empty] | Kazuya | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 |  | 124
[6 empty] | Taiyo | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 |  | 125
[6 empty] | Name3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 126
[6 empty] | Name4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 127
[6 empty] | Name5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 128
[6 empty] | Name6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 129
[6 empty] | Name7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 130
[6 empty] | Name8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 131
[6 empty] | Name9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 132
[6 empty] | Name10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 133
[6 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 134
135
[5 empty] | Team | 6 | [20 empty] | 136
[7 empty] | 0 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 |  | 137
[6 empty] | Average Assigned | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 138
[6 empty] | On-Track Line | 8 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | 139
[7 empty] | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 |  | 140
141
[7 empty] | 2023-11-12 | 13/11 | 14/11 | 15/11 | 16/11 | 17/11 | 18/11 | 19/11 | 20/11 | 21/11 | 22/11 | 23/11 | 24/11 | 25/11 | 26/11 | 27/11 | 28/11 | 29/11 | 0 |  | 142
| Total Hours | 48 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 143
| Hours 2 Days Ago | 48 |  |  |  |  | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 |  | 144
| Hours Today | 48 |  |  |  | Burndown Velocity |  | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 |  | 145
| Today | 0 |  |  |  | BDV | 0 | [19 empty] | 146
147
148
149
150

## Daily Scrum
2023-11-13 |  | Team Members
Dates |  | Kazuya | Taiyo | Name3 | Name4 | Name5 | Name6 | Name7 | Name8 | Name9 | Name10 | Workday
13/11 | Mon | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | 1
2023-11-14 | Tue | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | T: -- N: -- H: -- | 1
2023-11-15 | Wed | [10 empty] | 1
2023-11-16 | Thu | [10 empty] | 1
2023-11-17 | Fri | [10 empty] | 1
2023-11-18 | Sat | [10 empty] | 0
2023-11-19 | Sun | [10 empty] | 0
2023-11-20 | Mon | [10 empty] | 1
2023-11-21 | Tue | [10 empty] | 1
2023-11-22 | Wed | [10 empty] | 1
2023-11-23 | Thu | [10 empty] | 1
2023-11-24 | Fri | [10 empty] | 1
2023-11-25 | Sat | [10 empty] | 0
2023-11-26 | Sun | [10 empty] | 0
2023-11-27 | Mon | [10 empty] | 1
2023-11-28 | Tue | [10 empty] | 1
2023-11-29 | Wed | [10 empty] | 1
2023-11-30 | Thu | [10 empty] | 1
2023-12-01 | Fri | [10 empty] | 1
2023-12-02 | Sat | [10 empty] | 0
2023-12-03 | Sun | [10 empty] | 0
2023-12-04 | Mon | [10 empty] | 1